## Sheet1
Serial number | Task | Timeline |  | Status | Comment(if Any)
|  | Start time | End time
Start of Phase 1
1 | Research and analysis | 10th Feb | 12th Feb | Done
2 | Created github project link | 13th Feb | 13th Feb | Done
3 | Documentation | 14th Feb | 14th Feb | Done
End of Phase 1
Start of Phase 2
4 | Research on data collection | 15th Feb | 17th Feb | Done
5 | Data collection starts using TWEEPY | 18th Feb | 20th Feb | Done
6 | Report on data collection | 20th Feb | 20th feb | Done
7 | Documentation | 21st Feb | 22nd Feb | Done
End of Phase 2
Start of Phase 3
8 | Create MapReduce Job | 23rd feb | 17thMarch | Done
9 | Create HTML document on MapReduce jobs | 18th March | 19th March | Done
10 | Analysis of data as per the research | 18th March | 19th March | Done
End of Phase 3
Start of Phase 4
11 | Complete the remaining implementation | 20nd March | 31st March
12 | Genrerating graph using python library | 1st April | 5th April
13 | Testing on implementation | 1st April | 5th April
14 | Final documentation | 5th April | 10th April
End of Phase 4